## Slide 1
Sixth Meeting of the
Monitoring Committee of
OP “Transport and Transport infrastructure”
2014-2020
29 November 2016
Sofia

## Slide 2
Title of the priority axis | Total budget (euro) | Grant awarded (euro) | Paid expenditure (euro) | Certified expenditure (euro) | AF submitted/ approved *
1. Development of railway infrastructure along the “main” Trans-European Transport Network | 673 345 449 | 19 316 926 (2,9%) | 130 678 (0,02%) | - | 4/2
2. Development of road infrastructure along the “main” and “enlarged” Trans-European Transport Network | 673 345 448 | 438 302 964 (65,1%) | 56 820 223 (8,4%) | - | 4/2
3. Improving the intermodality of transport of passengers and cargo and development of sustainable urban transport” | 425 058 824 | 361 264 466 (85,1%) | 82 406 348 (19,4%) | 73 110 114 (17,2%) | 3/2
4. Innovations in management and services | 68 170 108 | 3 142 660 (4,6%) | 622 950 (0,9%) | 465 292 (0,7%) | 2/1
5. Technical assistance | 47 667 431 | 19 153 020 (40,2%) | 223 804 (0.5%) | 223 804 (0.5%) | 17/10
Total: | 1 887 587 260 | 841 622 047 (44.6%) | 140 204 003 (7,4%) | 99 730 105 (5,2%) | 30/17*
Status of implementation of the OPTTI 2014-2020
(by 15 November 2016)
* Total number AF submitted – 30; approved - 17, 6 of which for investment projects and 11 on technical assistance

## Slide 3
Project/ Beneficiaries: National Railway Infrastructure Company (NRIC) (673 345 449 евро) | Overall budget/ Grant awarded (euro) | Contracts eligible under OPTTI (euro) | Paid expenditure (euro) | State of AF (submitted/ approved
Infrastructure projects |  |  |  | 
1. Modernization of the substations along the railway Plovdiv – Burgas (phased by OPT) small-scale project | 10 910 533 / 9 092 111 | 9 292 833 | 130 678 | approved – Grant contract
2. Construction of four overhead passages along the railway section Septemvri – Plovdiv (phased by OPT) – small-scale project | 12 233 988 / 10 224 815 |  | - | approved – Grant contract
3. Rehabilitation of the railway line „Plovdiv-Burgas“, Phase 2 - major project | 411 106 379 | 35 712 873 | - | returned for corrections
Technical assistance |  |  |  | 
1. TA for railway section Sofia –Pernik - Radomir - Border with Macedonia | 16 011 039 | - | - | submitted
Total | 19 316 926 (2,9%) | 45 005 706 (6,7%) | 130 678 (0,02%) | 4/2
PA 1 “Development of railway infrastructure along the “main” Trans-European Transport Network”
(by 15 November 2016)
Ongoing projects: Modernization of traction substations (13/08/2015); Rehabilitation of the railway section "Skutare - Orizovo" worth 32.5 mln. euro (07/11/2016)

## Slide 4
Project/ Beneficiaries: Road Infrastructure Agency (RIA) (673 345 449 euro) | Overall budget/ Grant awarded (euro) | Contracts eligible under OPTTI (euro) | Paid expenditure (euro) | State of AF (submitted/ approved
Infrastructure projects |  |  |  | 
1. Struma MW, Lot 3.1, Lot 3.3 and “Zheleznica” tunnel - major project | 377 970 129 / 377 970 129* | 242 011 127 | 23 327 578 | returned for corrections
2. Construction “Western arc of the Sofia ring road“ – phase/ Section 2 (phased from OPT) – small project | 59 142 010 / 59 007 567 | 59 007 567 | 33 492 645 | Completed
Technical assistance |  |  |  | 
1. Preparation of the investment project - “Cherno more“ MW | 1 325 268 / 1 325 268 |  | - | approved
2. Preparation of the investment project “Ruse - Veliko Turnovo “MW | 2 598 180 | - | - | submitted
Total | 438 302 964 (65,09%) | 301 018 694 (44,70%) | 56 820 223 (8,44%) | 4/2
PA 2 “Development of road infrastructure along the “main” and “enlarged” Trans-European Transport Network”
(by 15 November 2016 )
* Grant Contract Awarded before AF approval based on МС Decision from Sept. 2015
Ongoing projects: Struma MW, Lot 3.1 (30.12.2015); Struma MW, Lot 3.3 (25.09.15)
Completed projects: “Western arc of the Sofia ring road“ , Phase 2 – completed (13.09.2016)

## Slide 5
* Project is approved with EC Decision dated 26.04.2016 with eligible costs up to 484 080 000 euro.
Ongoing projects: Construction of metro Line 3 of Sofia metro – sections, consultancy services, depot and metro trains (28.09.2015);
Completed projects: Extension of metro Line 2 of Sofia metro – completed (20.07.2016)
Project/ Beneficiaries: Metropoliten; National Railway Infrastructure Company (NRIC) (425 058 824 euro) | Overall budget/ Grant awarded (euro) | Contracts eligible under OPTTI (euro) | Paid expenditure (euro) | State of AF submitted/ approved
1. Construction of Line 3 of Sofia Metro: Stage I, “bul. Vl. Vazov - Jitnitza"- major project | 520 096 000 / 350 000 000 | 397 557 519 | 74 465 746 | approved – Grant contract*
2. Extension of Line 3 of Sofia Metro: Stage II, „Jitnitza – Ovcha Kupel – Ring road ” – major project | 110 600 000 / - | - | - | submitted
3. Extension of metro Line 2 (from MS “James Bouchier” to MS “Vitosha”) – small project | 13 514 905 / 11 264 466 | 11 264 466 | 7 940 602 | Completed
Total | 361 264 466 (85,1%) | 408 821 985 (96,1%) | 82 406 348 (19,4%) | 3/2
PA 3 “Improving the intermodality of transport of passengers and cargo and development of sustainable urban transport”
(by 15 November 2016 )

## Slide 6
Project/ Beneficiaries: NRIC, RIA, Metropoliten JSC, BPI Co., EA EMDR, BMTC, CAA (68 170 108 euro) | Overall budget/ Grant awarded (euro) | Contracts eligible under OPTTI (euro) | Paid expenditure (euro) | State of AF submitted/ approved
1. Improving the systems for navigation and layout-measurements on the Danube river - small-scale project (EA EMDR) | 3 142 660 / 3 142 660 | 3 105 352 | 622 950 | approved – Grant contract
2. ITS development and deployment within the scope of Trakia MW (RIA) | 4 463 480 / | - | - | submitted
Total | 3 142 660 (4,6%) | 3 105 352 (4,5%) | 622 950 (0,9%) | 2/1
PA 4 „ Innovations in management and services – introduction of modernized infrastructure for traffic management, increasing the transport safety and security”
(by 15 November 2016)
Ongoing projects: “Improving the systems for navigation and topo-hydrographic measurements on the Danube river” (11.03.2016 )
PA 5 Technical assistance
17 AF submitted 17 AF and 10 approved; The projects are to cover labor remuneration, training costs, publicity, etc .; Other projects: "Quantitative Risk Assessment" and "Integrated Information System for Planning and Resource Management" (BPIC) and "Development of an Integrated Transport Strategy” (MA).

## Slide 7: Indicative timetable for the implementation of major project 2014-2020 programming period
 |  | 2015 |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | 
 |  | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
PA 1 | 1. Modernization of the railway section “Elin Pelin–Ihtiman – Kostenetz” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2. Rehabilitation of the railway line „Plovdiv-Burgas“, Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PA 2 | 1. Struma MW, Lot 3.1, Lot 3.3 and “Zheleznitsa” tunnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2. Struma MW, Lot 3.2 “Krupnik - Kresna” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PA 3 | 1. Construction of Line 3 of Sofia metro: Stage I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2. Construction of Line 3 of Sofia metro: Stage ІI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 8: Upcoming activities OPTTI 2014-2020
  On 26.10.2016, the EC approved the first amendment of the OPTTI 2014-2020
  Until 15 December 2016 a Report on Certification will be submitted worth 37 mln. euro (16 million. euro from CF; 16 mln. euro from ERDF and 5 mln. euro from the NF)
  Submitting AF to the EC for ‘major' projects
  - Rehabilitation of the railway line „Plovdiv-Burgas“ - first quarter of 2017
  - Modernization of the railway section “Elin Pelin – Kostenetz” - first quarter of 2017
  - Construction of "Struma“ MW Lot 3.1, 3.3 and Jeleznitsa Tunnel –
  second quarter of 2017
  - Construction of "Struma“ MW, Lot 3.2 - fourth quarter of 2017
  - Construction of Line 3 of Sofia Metro: Stage II - first quarter of 2017
  Working with IFIs
  - EIB and NRIC - Support on the planning and implementation of projects for funding under PA4: GSM-R and ERTMS implementation; Train Operation Control System; Integrated ticketing and access to the train system, etc.
  - A potential technical assistance from the EIB to the OPTTI MA

## Slide 9: Conclusions
  Overall delay in the submissions of AF for PA 4 „Innovations in management and services“ (only 2 AF submitted)
  Lagging behind the schedule for conducting the tender procedures on investment projects (RIA and NRIC)
Continued difficulties and problems associated with implementation of new legislation (Act Funds Management ESIFs, Public Procurement Act and working with EUMIS 2020 )
  Intermediate targets for 2018 (financial index and stage performance); performance review in 2019 and the distribution of 'performance reserve‘
  Implementation of the ex-ante conditionalities for thematic objective 7 for sector “Transport

## Slide 10
Implementation of the ex-ante conditionalities for thematic objective 7 (condition is partially fulfilled)
On January 13, 2016 a contract was signed for "Development of an Integrated Transport Strategy (ITS) 2030" with the Contractor “Infracare - PTV” with implementation period of 14 months from the date of signature
Development of tools for modeling transport will be a major part of the preparation of ITS. Integrated national transport model will be based on a multimodal approach to forecasting demand for passenger and freight. The scope of the strategy document will cover all modes of transport and travel to, from and in Bulgaria
Currently presented by the contractor and approved by the contracting authority are:
  Inception report;
  Report "Creating an electronic database and preparation of the National Transport Model“;
  Report "Results of analysis“.
  Approved reports are available at http://optransport.bg/page.php?c=286&d=1618
Report "Objectives and Measures“ is in the process of coordination and approval
Forthcoming submission of Report ‘Assessment of the administrative capacity'

## Slide 11: Implementation of the ex-ante conditionalities for thematic objective 7 (condition is partially fulfilled)
On 10/21/2016 MOEW was notified in accordance with the provisions of the Law on Environmental Protection and the Regulation on conditions and procedures for environmental assessment of plans and programs. On 10/11/2016 MTITC received opinion from the MOEW
By the end of 2016 there will be a version of the ITS, which will contain the main elements:
  The electronic database on which to develop the National Transport Model
  Analyses of different modes of transport in compliance with the preconditions in the "Transport" and results
  Strategic objectives and priorities of transport policy until 2030
  Specific measures
  The results of the review of the administrative capacity of beneficiaries
  The identified projects
  National transport model
  Strategic Environmental Assessment will be ready in March 2017 and then the approval of ITS by Council of Ministers of the Republic of Bulgaria is expected

## Slide 12: Indicative Annual Work Program for 2017 of OPTTI 2014-2020
The draft of the Indicative annual work program (IAWP) for 2017 of OPTTI 2014-2020 was published on September 30, 2016 for a preliminary discussion on the website of the program and the single information portal for general information about the management of ESIFs
In the 20-day period to discuss the draft IAWP for 2017 comments were received from the concrete beneficiaries: Metropolitan, BPI and CAA
IAWP for 2017 is in accordance with the approved OPTTI and procedures for the award of grants announced on September 1, 2015, covering the full budget of the program. In IAWP for 2017 budget is allocated to the categories of intervention, taking into account the free financial resources in procedures to October 2016
IAWP for 2017 of OPTTI was approved by the Council for coordination of the management of EU funds at a meeting held on 11.11.2016