## Slide 1: “Lessons Learnt” workshop on 18th June, Sofia
Project Implementation Support Service Agreement (PISSA) TA2013040 BG BSF
S3: “Assessment, management and pricing of risks (including reliable cost evaluation)”
Tamás Kozák, EIB Risk Manager, Sofia

## Slide 2: The Goals
Remedial Action (Risk Response) Plan as regard the 3 railway projects at risk
Identify those risks which hazard the project completions by end of 2015
Working out the risk governance system to monitor the crucial risks

## Slide 3: Risk definition to the project
Combined effect at the probability of occurrance of
the undesirable event and
the magnitude of the event , the possibility of loss or injury .
/see later the more concrete terminologies to the project/

## Slide 4: Project Phases
Part1: Risk Management and Activity Overview
Part 2: Risk Identification
Part 3: Risk Analysis
Part 4: Risk Response Planning
Part 5: Risk Monitoring and Control

## Slide 5: Risk Management and Activity Overview
1. PLOVDIV – SVILENGRAD RAILWAY LINE (BG161PO004-1.0.01-0005) PROJECT
Section I Dimitrovgrad rail station
Section III Simeonovgrad rail station
Additional Signalling system, OHL catenary
2. SEPTEMVRI - PLOVDIV RAILWAY LINE (BG 161 PO 004-1.0.01-0008) PROJECT
Position 2 Pazardjik – Stamboliiski (38,2 km)
Additional Signalling system, OHL catenary
3. PLOVDIV – BURGAS RAILWAY LINE (BG 161 PO 004-1.0.01-0007) PROJECT (OPTIONAL)
Position 3 Tserkovski – Karnobat – Burgas (152 km)

## Slide 6: Risk Identification
The components of risk register:
Threat: Category which helps to identify potential sources of risk to the project
Blocking Cause: The activity or the missing of the activity which gives rise the risk:
Risk: This is a negative consequence which cause uncertain in project completion.
Effect: The result of evaluation which shows the severity of the risk.
Source of Information: Documentation, meeting, etc.

## Slide 7: Risk Identification - Example
Bureaucracy in the land acquisition processes - LEGAL
Due to heavy rains - ENVIRONMENT
STAKEHOLDER requirement
Improperly trained workforce about FIDIC requirements
Communication problem among constructor - engineer - employer
As a result of environmental impact
Due to constructing in congested industrial area
Due to poor project management by the general constructor
Due to lump sum contract

## Slide 8: Risk Analysis
UNDESIRABLE EVENT: COMPLETION DATE > 12.31.2015 - suggestion
SIGNIFICANT COST: PLAN – ACTUAL GAP OR CANCELLED TENDER CASH > 15% - suggestion

## Slide 9: Risk Response Planning
Avoid – eliminate the cause
Mitigate – reduce the impact or probability of occurrence
Transfer – assign the risk to 3rd party
Accept – contingency plan or nothing

## Slide 10: Risk Monitoring and Control I.
Reserve at Start – Used Reserve = Reserve Balance

## Slide 11: Risk Monitoring and Control II.
Risk Response Plan
Completion date >;< 31.12.2015
Budget – Actual Cost Gap > 15 %
Corrective action
Refine or adjustment of Project Plan

## Slide 12: Summary for Risk Governance
Roles and Responsibilities
Policies, Procedures
Creation of Metrics
Monitor Risk Response Plan
Systematize the regular monitoring and reporting process

## Slide 13: Summary for Lessons Learned
„what went right”
  Started to identify the crucial risks
„what went wrong”:
  What should have been earlier
„what should be done differently”:
  Regular risk monitoring in future